JPV BOOTCAMP

# JPV Bootcamp Platform Expansion & Go-Live Plan

Client implementation plan, progress comparison, delivery timeline, decisions and launch expectations

Version 3.7 • Updated implementation progress and front-end delivery timeline • 17 July 2026

What changed since Version 3.4 Version 3.4 recorded the Free/Pro refit, checkout hardening, migration-readiness checks and front-end milestone. Version 3.7 records the M0/M1 implementation state and the programme-content readiness packet: local release validation is complete, but content approval and external cutover gates remain open.

ON SCHEDULE — FIRST RELEASE 22 JULY 2026 First release: 22 July 2026 front-end/staging-public review. Handover: 23 July; client finished-by: 24 July. Launch-scoped implementation and local release/browser validation are complete. Full platform cutover remains conditional on client content/copy, staging smoke, provider/email, migration, rollback and final acceptance gates.

Main action Approve the hardening-first sequence, provide the 15 July content and billing/legal decisions, and keep the 22 July front-end milestone conditional. Do not apply migrations until target-environment approval, rehearsal and rollback evidence are complete.

| Item | Version 3.7 summary |
| --- | --- |
| Document purpose | Client-facing update that keeps the Version 3.4 format and records current Version 3.7 staging-branch progress, including updated progress, timeline and launch dependencies. |
| Progress delivered | 100% of planned launch-scoped M0/M1 implementation packets are complete, including the launch surfaces and programme-content acceptance tooling. The ~74% figure is the rebased share of the larger expanded roadmap, not a regression from Version 3.4. Local release/browser validation is complete; external approvals remain open. |
| Go-live approach | The front-end milestone stays targeted for 22 July only if public acceptance and client content/copy approval pass. Full platform go-live remains conditional on smoke, provider/email, migration, rehearsal, rollback and approval evidence. |

# 1. Executive summary

Version 3.7 is not a scope reset. It is a progress update from the Version 3.4 client plan. The platform direction remains the same: one paid membership, monthly no-minimum-commitment and annual payment options, controlled Free/support access, public landing page, member portal, billing automation, course access, partner/community follow-up and a controlled migration/cutover path.

The major difference is that the launch-scoped M0/M1 surfaces and the programme-content acceptance tooling now exist. Remaining work is client content and approval, migration approval and rehearsal, provider/email verification, staging smoke, rollback evidence and formal go/no-go review.

READ THIS FIRST — WHY THE PERCENTAGE LOOKS LOWER Version 3.4 measured the expanded launch after the large Free/Pro staging refit and operator-preflight work. Version 3.7 records current progress after portal-aligned MVP implementation and auth hardening. The lower percentage is a scope rebase, not a loss of progress; it does not mean migrations are approved or applied.

# 2. Version 3.4 baseline vs Version 3.7 current progress

| Area | Version 3.4 baseline | Version 3.7 rebased progress | How to read it |
| --- | --- | --- | --- |
| Overall expanded platform | ~73% for the expanded platform. | ~74% | MVP surfaces and repository content controls exist; approved content, provider checks and cutover approval remain incomplete. |
| Core staging readiness | ~97% for core staging readiness. | ~86% | Core services and local release gates pass; migration, provider, smoke and runtime acceptance evidence remain. |
| Build foundation | ~89% current build foundation. | ~88% | Typed foundations and launch-scoped tests are present; preview-only and deferred workflows remain clearly bounded. |
| Testing/release readiness | ~94% current testing/release readiness. | ~82% | Local release validation covers `138/138` checks and browser E2E covers `58/58` desktop/mobile tests; staging/provider evidence remains. |
| Migration readiness | ~60% current migration readiness. | ~60% | Unchanged: approval, rehearsal and execution remain pending. |
| Live cutover readiness | ~22% live cutover readiness. | ~22% | Unchanged: cutover still depends on approval, provider/email verification, staging smoke and content. |

# 3. What is complete in the current staging version

• Feature branch is `feature/course-branding-and-preview`, the staging / production-staged deployment target.

• Payload-only Free/Pro refit is committed, pushed, clean and validated.

• Root feature pages are compatibility redirects; member/student features are aligned under `/portal` and admin/operator review under `/admin`.

• Partner referral and community interaction remain preview/deferred surfaces; support/pay-it-forward has a repository-owned durable intake path; the 8-week programme remains preview-only while the repository content intake and acceptance controls await the client package.

• Programme and community member-content routes require portal member authentication.

• WordPress, FluentCRM, FluentCommunity, old portal, VIP and exhibitor active paths have been removed or confined to documented negative-rule / migration exceptions.

• Checkout is Pro-only with monthly/annual payment options; rejected legacy plan values are covered.

• Migration approval, rehearsal, staging smoke, provider/email and evidence templates are prepared, but no migration, complete smoke run or provider acceptance is complete.

• Evidence tooling, pinned `pnpm@10.33.0` checks, the `138/138` release gate and `58/58` desktop/mobile browser E2E are in place; staging and provider evidence remain external gates.

Current branch status Current validated branch tip for this document: 8927df9 docs: checkpoint membership implementation readiness. No migrations have been applied.

# 4. Version 3.7 progress by roadmap phase

The percentages below are estimates for the expanded platform after the roadmap scope was enlarged. They are rebased delivery-readiness indicators, not evidence of lost progress or a guarantee that live cutover can happen without the remaining approval and evidence steps.

| Area / phase | Version 3.4 | Version 3.7 rebased | Progress reading | Evidence | Remaining blocker |
| --- | --- | --- | --- | --- | --- |
| Overall expanded platform | ~73% | ~74% | Rebased scope; not a regression | Core auth, billing, access and migration foundations plus new prototype surfaces audited. | P0 hardening, operational integration, content, provider checks and cutover approval. |
| Core staging readiness | ~97% | ~86% | Rebased scope; not a regression | Auth, account security, entitlement, billing projection and release safeguards are substantial. | Public admin route, endpoint hardening, dependency advisories, complete smoke and provider evidence. |
| Build foundation | ~89% | ~88% | Rebased scope; not a regression | Most domains have typed service foundations and focused tests. | Approved content, provider checks, staging smoke and formal cutover evidence. |
| Testing / release readiness | ~94% | ~82% | Rebased scope; not a regression | Local release, browser, TypeScript, build and Prisma validation evidence is available. | Staging smoke, provider/email verification, migration approval, content approval and final go/no-go remain. |
| Migration readiness | ~60% | ~60% | Unchanged | Migration sources and approval docs exist; 11-migration inventory checked. | Table-plan-to-Free and account-column approval, apply path, backup, rehearsal and rollback review. |
| Live cutover readiness | ~22% | ~22% | Unchanged | Handoff and evidence templates exist. | No migrations, complete smoke, provider/email acceptance, content acceptance or final approval. |

# 5. Detailed delivery phases and current status

| Phase | Version 3.7 readiness | Dates / milestone | Goal | Go-live impact |
| --- | --- | --- | --- | --- |
| A Decisions & final scope check | Approx. 65% | 7–9 July, continuing where approval is still open | Keep Free/Pro scope locked, confirm remaining business approvals and prevent drift. | Required before migration/cutover; incomplete approvals can move the launch. |
| B Membership & billing automation | Approx. 78% | 8–15 July | Pro monthly/annual checkout, failed-payment behaviour, billing readiness and access rules. | Core launch requirement; code is hardened, provider/live checks remain. |
| C Public landing page / front end | Approx. 70% | 9–22 July | Bright one-page landing page plus portal-aligned member routes, clear Pro membership and support/pay-it-forward calls to action. | Frontend go-live milestone is 22 July; client finished-by date is 24 July; handover buffer by 23 July. |
| D Course/content + video decision | Approx. 45% | 10–18 July; client input due 15 July | Use the canonical intake contract for the representative 8-week package; the repository validation and import-plan path is ready. | Core launch requirement; depends on the client package and approval evidence arriving by the communicated 15 July input date. |
| E Migration + core go-live | Approx. 55% | 18–24 July | Approval, rehearsal, rollback plan, target-environment verification and core go-live decision. | Go-live cannot proceed until approval and rehearsal evidence are complete. |
| F Partner/community preview | Approx. 45% | 25–31 July | Partner tracking/forms/reporting and community/private-room preview. | Can follow core launch unless made launch-critical. |
| G Advanced features/live calls | Approx. 10% | August onward | Private messaging, digests, advanced notifications and live calls. | Post-core unless explicitly promoted. |

# 6. Front-end website delivery update

FRONT-END DELIVERY HIGHLIGHT Client requirement: the front end of the website should be finished on 24 July 2026. To protect that date, the internal delivery/handover target is 23 July 2026 and the front-end go-live milestone remains 22 July 2026.

The front-end timeline remains conditional on client content/copy acceptance and the independent operator gates. Local release, browser, build and schema validation now pass; full migration/cutover remains a separate approval decision.

| Date | Milestone | Owner | Dependency / note |
| --- | --- | --- | --- |
| 15 July 2026 (Wednesday) | Client content and information delivery | Client | Final public wording, support/pay-it-forward copy, proof/trust items, course/content inputs and any missing pricing language should arrive here to protect 22–24 July. |
| 16–18 July 2026 | Front-end test and final copy polish | Steve + Client | Use approved content or confirm placeholder copy where final copy is not ready. |
| 22 July 2026 | Front-end website go-live milestone | Steve | Public-facing landing/front-end should be ready for staging/public review with the new membership offer. |
| 23 July 2026 | Delivery/handover buffer | Steve + Client | Buffer day for client review, final notes and non-migration polish before the client’s required finished-by date. |
| 24 July 2026 | Client-required finished-by date | Client + Steve | The front end should be finished by this date. This is not approval to apply migrations. |

Delivery rule The communicated 22 July milestone, 23 July handover buffer and 24 July finished-by date remain conditional on approved content/copy and the independent migration, rehearsal, rollback, provider/email, staging-smoke and final-acceptance gates.

# 7. Membership, pricing and support access

Version 3.7 keeps the clarified offer: one paid JPV Bootcamp Membership with monthly no-minimum-commitment and annual payment options. Free access remains controlled non-paid access for approved support, staff/admin cases and pay-it-forward flows; it is not a public free product tier.

| Decision | Version 3.7 current answer | Status |
| --- | --- | --- |
| Public membership | Show one paid membership: Pro / JPV Bootcamp Membership. | Implemented in code/docs; final wording still client-visible. |
| Monthly payment | £80/month with no minimum commitment. | Monthly Pro path and commitment wording are covered locally; live provider checks remain. |
| Annual payment | £800 upfront for a 12-month service period. | Pro annual path is covered locally; live provider checks remain. |
| Free/support access | Controlled non-paid access only; not marketed as a public free tier. | Controlled Free semantics and repository intake controls exist; migration, provider and live seat-grant verification remain. |
| Old tiers | No active public VIP/exhibitor/old portal paths. | Removed from active paths; allowed exceptions are documented migration/negative-rule mentions. |

# 8. Migration approval and cutover status

The migration path is prepared but not approved for execution. The feature branch contains the migration sources and safety documentation needed for target-environment approval, but no migration has been applied.

| Approval item | Version 3.7 status | Why it matters |
| --- | --- | --- |
| Table-plan-to-Free mapping | Pending approval | Legacy table-plan values are intended to become controlled Free access, not a third paid product. |
| Account-column rename | Pending approval | Old account-reference columns are renamed to neutral account names without dropping records. |
| Approved migration path | Pending confirmation | Migrations must be run only through the approved database migration path. |
| Rollback/recovery review | Pending | A backup/snapshot and rollback owner must be confirmed before rehearsal/execution. |
| Staging smoke evidence | Pending | Operator evidence must be captured after the staging smoke run. |
| Provider/email live verification | Pending | Email provider and Stripe/live mode checks must be verified without leaking secrets. |

Hard stop Do not apply migrations without written target-environment approval. Do not treat the front-end go-live milestone as migration approval.

# 9. Acceptance plan for the 22–24 July window

| Area | Acceptance check | Version 3.7 status |
| --- | --- | --- |
| Public site / front end | Review the landing page and confirm offer, wording and calls to action. | Milestone set for 22 July; client inputs due 15 July and are still outstanding as of 17 July. |
| Membership checkout | Monthly and annual Pro checkout flows start correctly; legacy values fail safely. | Monthly/annual code paths and browser E2E pass locally; staging/provider smoke remains. |
| Billing recovery | Failed-payment emails and access rules behave as agreed. | Automated readiness exists; provider/email checks remain. |
| Member portal | Member can sign in, access the right course and manage account. | Portal auth and canonical member ownership are aligned locally; staging smoke remains. |
| Course pilot | 8-week structure, lessons, resources and progress are visible/editable. | The eight-week preview remains placeholder data; the deterministic intake, acceptance and import-plan path is ready, but approved content is required. |
| Migration rehearsal | Sample existing members map correctly to the new access model. | Pending approval and rehearsal. |
| Cutover rehearsal | Launch, pause and rollback plan are understood and accepted. | Pending approval and evidence. |

# 10. Version 3.7 timeline and phased go-live plan

The plan uses overlapping phases, but hardening now precedes feature expansion. The 22 July front-end milestone remains conditional on client content/copy acceptance; full 22–24 July cutover also depends on smoke, provider/email verification, migration approval, rehearsal and rollback evidence.

| Phase | 10–13 Jul | 14–17 Jul | 18–20 Jul | 21–24 Jul | 25–31 Jul | August |
| --- | --- | --- | --- | --- | --- | --- |
| A Scope | Public blockers Billing decision |  |  |  |  |  |
| B Billing | Decision | Implement + harden | Smoke |  |  |  |
| C Public site | Legal + copy | Harden | Test + content | 22 Jul go-live 23 Jul handover 24 Jul finished |  |  |
| D Course | Content prep | 15 Jul due Validate | Accept |  |  |  |
| E Migration |  | Approval prep | Rehearsal prep | Go-live only if approved |  |  |
| F Partner |  |  |  |  | Preview |  |
| G Advanced |  |  |  |  | Plan | Build |

# 11. Next steps

| Step | Owner | Target |
| --- | --- | --- |
| Provide final website/front-end content or approve placeholders. | Client | 15 July 2026, Wednesday. Still outstanding as of 17 July 2026. |
| Confirm membership wording, billing wording and support/pay-it-forward copy. | Client + Steve | By 15 July where possible; still outstanding as of 17 July before final front-end acceptance. |
| Run the approved programme-content acceptance and release-candidate evidence sequence, then complete the remaining staging and go/no-go gates. | Steve / operator | After the client package arrives; before the final 22–24 July launch decision. |
| Run staging smoke and capture evidence. | Steve + Client | Before final 22–24 July launch decision. |
| Complete provider/email live verification evidence. | Steve + Client | Before production-facing communication acceptance. |
| Approve table-plan-to-Free mapping and account-column rename. | Client / target-environment owner | Before any migration rehearsal or execution. |
| Run migration/cutover rehearsal and rollback review. | Steve + Client | Only after written approval. |
| Frontend website go-live milestone. | Steve | 22 July 2026. |
| Frontend handover buffer. | Steve + Client | 23 July 2026. |
| Client required front-end finished-by date. | Client + Steve | 24 July 2026. |

Final note Version 3.7 confirms strong core foundations and complete local release/browser validation. The programme remains preview-only until approved content is accepted; full cutover remains at risk until migration, provider/email, smoke, rollback and final approval evidence exist.

JPV Bootcamp Platform Expansion & Go-Live Plan Version 3.7 | Client review update